| Performance Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Performance |  |  |  |  |  | To-Complete |  |  |
|  | Task Details |  |  | Baseline |  |  |  | Actuals |  |  | Value to Cost |  |  |  | Variances |  |  |  |  |  |  | Forecasting (EAC) |  |  | Performance Index |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Index |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (TCPI) |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Planned | Earned | Actual | Cost |  | Schedule |  | Forecast Cost Schedule Budgeted |  |  |  |  | CPI | CPI & SPI | Based on | Based on |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BAC | EAC (CPI) |  |
|  |  |  |  |  |  |  |  |  |  |  | Value | Value | Cost |  |  |  |  |  |  |  |  | Rate |  |  |  |  |  |
|  |  |  |  |  | (%) | ($) |  |  |  | (%) | ($) | ($) | ($) | ($) | (%) | ($) | (%) | VAC | CPI |  | SPI | ($) | ($) | ($) |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (AC / |  | (SV / | (BAC - | (EV / |  |  | (AC + BAC | (BAC / | (AC + ((BAC - | ((BAC - | ((BAC - |  |
| ID | Task Name | Duration Start Finish Complete |  |  |  | (BAC) | Duration Start Finish Complete |  |  |  | (PV) | (EV) | (AC) | (CV) |  | (SV) |  |  |  |  | (EV / PV) |  |  |  | EV) / (BAC EV) / (EAC |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | EV) |  | PV) | EAC) | AC) |  |  | - EV) | CPI) | EV) / (CPI * SPI))) |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - AC)) | - AC)) |  |
|  | LullSIM | 131 | Jan |  |  |  | 137 | Jan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Localization |  |  | Jul 31 100% |  |  |  |  | Aug 8 100% |  | $373,502 | $373,502 | $385,125 ($11,623) |  | 103% | $0 | 0% | ($11,623) | 0.97 |  | 1.00 | $385,125 | $385,054 | $385,125 | 1.00 | 1.00 |  |
|  |  | days | 28 |  |  | $373,502 days |  | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Glossary | 16 days | Jan | Feb | 100% | $12,000 | 16 days | Jan | Feb | 100% | $12,000 | $12,000 | $11,520 | $480 | 96% | $0 | 0% | $480 | 1.04 |  | 1.00 | $11,520 | $11,538 | $11,520 | 1.00 | 1.00 |  |
|  |  |  | 28 | 19 |  |  |  | 28 | 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Localize French | 7 days | Jan | Feb 5 | 100% | $3,500 | 7 days | Jan | Feb 5 | 100% | $3,500 | $3,500 | $3,360 | $140 | 96% | $0 | 0% | $140 | 1.04 |  | 1.00 | $3,360 | $3,365 | $3,360 | 1.00 | 1.00 |  |
|  | Glossary |  | 28 |  |  |  |  | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Localize German | 7 days | Jan | Feb 5 | 100% | $3,500 | 7 days | Jan | Feb 5 | 100% | $3,500 | $3,500 | $3,360 | $140 | 96% | $0 | 0% | $140 | 1.04 |  | 1.00 | $3,360 | $3,365 | $3,360 | 1.00 | 1.00 |  |
|  | Glossary |  | 28 |  |  |  |  | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  | Jan |  |  |  |  | Jan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Japanese | 10 days |  | Feb 8 | 100% | $5,000 | 10 days |  | Feb 8 | 100% | $5,000 | $5,000 | $4,800 | $200 | 96% | $0 | 0% | $200 | 1.04 |  | 1.00 | $4,800 | $4,808 | $4,800 | 1.00 | 1.00 |  |
|  |  |  | 28 |  |  |  |  | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Glossary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Review French | 5 days | Feb | Feb | 100% | $0 | 5 days | Feb | Feb | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 |  | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |  |
|  | Glossary |  | 6 | 12 |  |  |  | 6 | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | Review German | 5 days | Feb | Feb | 100% | $0 | 5 days | Feb | Feb | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 |  | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |  |
|  | Glossary |  | 6 | 12 |  |  |  | 6 | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | Review Japanese | 5 days | Feb | Feb | 100% | $0 | 5 days | Feb | Feb | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 |  | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |  |
|  | Glossary |  | 12 | 18 |  |  |  | 12 | 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Correct French | 1 day | Feb | Feb | 100% | $0 | 1 day | Feb | Feb | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 |  | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |  |
|  | Glossary |  | 13 | 13 |  |  |  | 13 | 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 | Correct German | 1 day | Feb | Feb | 100% | $0 | 1 day | Feb | Feb | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 |  | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |  |
|  | Glossary |  | 13 | 13 |  |  |  | 13 | 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | Correct Japanese | 1 day | Feb | Feb | 100% | $0 | 1 day | Feb | Feb | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 |  | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |  |
|  | Glossary |  | 19 | 19 |  |  |  | 19 | 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| 16 | Software | 124 | Jan | Jul 22 100% |  | $82,252 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | days | 28 |  |  |  |  |
| 17 | Conduct Pseudo | 9 days | Jan | Feb 7 | 100% | $0 |  |
|  | Translation |  | 28 |  |  |  |  |
| 18 | Fix Pseudo | 2 days | Feb | Feb | 100% | $0 |  |
|  | Translation Errors |  | 8 | 11 |  |  |  |
| 19 |  |  |  |  |  |  |  |

| 130 | Jan | Jul 30 100% |  | $82,252 | $82,252 | $83,265 | ($1,013) | 101% | $0 | 0% | ($1,013) | 0.99 | 1.00 | $83,265 | $83,083 | $83,265 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| days | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 days | Jan | Feb | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 |  |
|  | 28 | 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 days | Feb | Feb | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 |  |
|  | 15 | 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- 1.00

- 1.00

- 1.00

|  | Localize French |  | Feb |  |  |  |  | Feb |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 20 | Code Freeze | 35 days |  | Apr 7 | 100% | $15,188 | 35 days |  | Apr 11 100% | $15,188 | $15,188 | $15,492 | ($304) | 102% | $0 | 0% | ($304) | 0.98 | 1.00 | $15,492 | $15,498 | $15,492 |  |
|  |  |  | 14 |  |  |  |  | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Software Files |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Localize German |  | Feb |  |  |  |  | Feb |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21 | Code Freeze | 35 days |  | Apr 7 | 100% | $15,188 | 35 days |  | Apr 11 100% | $15,188 | $15,188 | $15,492 | ($304) | 102% | $0 | 0% | ($304) | 0.98 | 1.00 | $15,492 | $15,498 | $15,492 |  |
|  |  |  | 14 |  |  |  |  | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Software Files |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22 | Japanese Code | 40 days | Feb | Apr 16 100% |  | $20,250 | 40 days | Feb | Apr 16 100% | $20,250 | $20,250 | $20,655 | ($405) | 102% | $0 | 0% | ($405) | 0.98 | 1.00 | $20,655 | $20,663 | $20,655 |  |
|  | Freeze Software |  | 20 |  |  |  |  | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Files

- 1.00

- 1.00

- 1.00

| 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Localize French | Apr |  |  | Apr | May |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 24 | Final Software 20 days |  | May 6 100% | $7,088 20 days |  |  | 100% | $7,088 | $7,088 | $7,088 | $0 | 100% $0 0% $0 | 1.00 1.00 | $7,088 | $7,088 | $7,088 | 1.00 | 1.00 |  |
|  |  | 8 |  |  | 14 | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |

PRO version  Are you a developer? Try out the HTML to PDF API	pdfcrowd.com

|  | Files |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Localize German |  | Apr |  |  |  |  | Apr | May |  |  |  |  |  |  |  |  |  |  |
| 25 | Final Software | 20 days |  | May 6 100% |  | $7,088 | 20 days |  |  | 100% | $7,088 | $7,088 | $7,088 | $0 | 100% | $0 | 0% | $0 |  |
|  |  |  | 8 |  |  |  |  | 14 | 12 |  |  |  |  |  |  |  |  |  |  |
|  | Files |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  | Apr | May |  |  |  | Apr | May |  |  |  |  |  |  |  |  |  |  |
| 26 | Japanese Final | 25 days |  |  | 100% | $9,450 | 25 days |  |  | 100% | $9,450 | $9,450 | $9,450 | $0 | 100% | $0 | 0% | $0 |  |
|  |  |  | 17 | 23 |  |  |  | 17 | 23 |  |  |  |  |  |  |  |  |  |  |
|  | Software Files |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| 1.00 | 1.00 | $7,088 | $7,088 | $7,088 | 1.00 | 1.00 |
| --- | --- | --- | --- | --- | --- | --- |
| 1.00 | 1.00 | $9,450 | $9,450 | $9,450 | 1.00 | 1.00 |

| 27 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 28 | Build French | 1 day | May | May 7 | 100% | $0 |  |
|  | Running Software |  | 7 |  |  |  |  |
| 29 | Build German | 1 day | May | May 7 | 100% | $0 |  |
|  | Running Software |  | 7 |  |  |  |  |
| 30 | Build Japanese | 1 day | May | May | 100% | $0 |  |
|  | Running Software |  | 27 | 27 |  |  |  |

| 1 day | May | May | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 13 | 13 |  |  |  |  |  |  |  |  |  |  |
| 1 day | May | May | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  | 13 | 13 |  |  |  |  |  |  |  |  |  |  |
| 1 day | May | May | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  | 27 | 27 |  |  |  |  |  |  |  |  |  |  |

| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| --- | --- | --- | --- | --- | --- | --- |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |

| 31 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Review French |  | May May |  |  |  |  | May May |  |  |  |  |  |  |  |  |  |  |  |
| 32 | Localized | 5 days |  |  | 100% | $2,400 | 5 days |  |  | 100% | $2,400 | $2,400 | $2,400 | $0 | 100% | $0 | 0% | $0 |  |
|  |  |  | 8 | 14 |  |  |  | 14 | 20 |  |  |  |  |  |  |  |  |  |  |
|  | Software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review German |  | May May |  |  |  |  | May May |  |  |  |  |  |  |  |  |  |  |  |
| 33 | Localized | 5 days |  |  | 100% | $2,400 | 5 days |  |  | 100% | $2,400 | $2,400 | $2,400 | $0 | 100% | $0 | 0% | $0 |  |
|  |  |  | 8 | 14 |  |  |  | 14 | 20 |  |  |  |  |  |  |  |  |  |  |
|  | Software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review Japanese |  | May |  |  |  |  | May |  |  |  |  |  |  |  |  |  |  |  |
| 34 | Localized | 5 days |  | Jun 3 | 100% | $3,200 | 5 days |  | Jun 3 | 100% | $3,200 | $3,200 | $3,200 | $0 | 100% | $0 | 0% | $0 |  |
|  | Software |  | 28 |  |  |  |  | 28 |  |  |  |  |  |  |  |  |  |  |  |
| 35 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | QA French |  | May May |  |  |  |  | May May |  |  |  |  |  |  |  |  |  |  |  |
| 36 | Localized | 5 days |  |  | 100% | $0 | 5 days |  |  | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  |  |  | 8 | 14 |  |  |  | 14 | 20 |  |  |  |  |  |  |  |  |  |  |
|  | Software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | QA German |  | May May |  |  |  |  | May May |  |  |  |  |  |  |  |  |  |  |  |
| 37 | Localized | 5 days |  |  | 100% | $0 | 5 days |  |  | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  |  |  | 8 | 14 |  |  |  | 14 | 20 |  |  |  |  |  |  |  |  |  |  |
|  | Software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | QA Japanese |  | May |  |  |  |  | May |  |  |  |  |  |  |  |  |  |  |  |
| 38 | Localized | 5 days |  | Jun 3 | 100% | $0 | 5 days |  | Jun 3 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  | Software |  | 28 |  |  |  |  | 28 |  |  |  |  |  |  |  |  |  |  |  |
| 39 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Implement French |  | May May |  |  |  |  | May May |  |  |  |  |  |  |  |  |  |  |  |
| 40 | Software | 5 days |  |  | 100% | $0 | 5 days |  |  | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  |  |  | 15 | 21 |  |  |  | 21 | 27 |  |  |  |  |  |  |  |  |  |  |
|  | Corrections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Implement |  | May May |  |  |  |  | May May |  |  |  |  |  |  |  |  |  |  |  |
| 41 | German Software 5 days |  |  |  | 100% | $0 | 5 days |  |  | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  |  |  | 15 | 21 |  |  |  | 21 | 27 |  |  |  |  |  |  |  |  |  |  |
|  | Corrections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Implement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 42 | Japanese | 5 days | Jun | Jun 10 100% |  | $0 | 5 days | Jun | Jun 10 100% |  | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  | Software |  | 4 |  |  |  |  | 4 |  |  |  |  |  |  |  |  |  |  |  |
|  | Corrections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 43 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 44 | Build French Beta | 1 day | Jun | Jun 24 100% |  | $0 | 1 day | Jul 1 Jul 1 |  | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  | Version |  | 24 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 45 | Build German | 1 day | Jun | Jun 24 100% |  | $0 | 1 day | Jul 1 Jul 1 |  | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  | Beta Version |  | 24 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 46 | Build Japanese | 1 day | Jun | Jun 23 100% |  | $0 | 1 day | Jun | Jun 27 100% |  | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  | Beta Version |  | 23 |  |  |  |  | 27 |  |  |  |  |  |  |  |  |  |  |  |
| 47 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct |  | Jun |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 48 | Functional QA of | 10 days |  | Jul 8 | 100% | $0 | 10 days | Jul 2 Jul 16 |  | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  |  |  | 25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | French Beta |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct |  | Jun |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 49 | Functional QA of | 10 days |  | Jul 8 | 100% | $0 | 10 days | Jul 2 Jul 15 |  | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  |  |  | 25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | German Beta |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct |  | Jun |  |  |  |  | Jun |  |  |  |  |  |  |  |  |  |  |  |
| 50 | Functional QA of | 10 days |  | Jul 7 | 100% | $0 | 10 days |  | Jul 11 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 |  |
|  |  |  | 24 |  |  |  |  | 30 |  |  |  |  |  |  |  |  |  |  |  |

| 1.00 | 1.00 | $2,400 | $2,400 | $2,400 | 1.00 | 1.00 |
| --- | --- | --- | --- | --- | --- | --- |
| 1.00 | 1.00 | $2,400 | $2,400 | $2,400 | 1.00 | 1.00 |
| 1.00 | 1.00 | $3,200 | $3,200 | $3,200 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |

PRO version  Are you a developer? Try out the HTML to PDF API	pdfcrowd.com

Japanese Beta

51

- Implement French 4 days Beta Corrections

Implement

53	German Beta 4 days Corrections

Implement

54	Japanese Beta 4 days Corrections

55

Build French

56	Release 1 day Candidate

Build German

57	Release 1 day Candidate

Build Japanese

58	Release 1 day Candidate

59

Review French

60	Release 3 days Candidate

Review German

61	Release 3 days Candidate

Review Japanese

62	Release 3 days Candidate

63

Implement French

64	Release 1 day Candidate

Corrections

Implement

- German Release 1 day Candidate

Corrections Implement

Japanese

66	Release 1 day Candidate

Corrections

67

- Build French Gold 1 day Master

| 69 | Build German | 1 day |  |
| --- | --- | --- | --- |
|  | Gold Master |  |  |
| 70 | Build Japanese | 1 day |  |
|  | Gold Master |  |  |
| 71 |  |  |  |

| Jul 9 Jul 14 |  | 100% |  |
| --- | --- | --- | --- |
| Jul 9 Jul 14 |  | 100% |  |
| Jul 8 Jul 11 |  | 100% |  |
| Jul | Jul 15 | 100% |  |
| 15 |  |  |  |
| Jul | Jul 15 | 100% |  |
| 15 |  |  |  |
| Jul | Jul 14 | 100% |  |
| 14 |  |  |  |
| Jul | Jul 18 | 100% |  |
| 16 |  |  |  |
| Jul | Jul 18 | 100% |  |
| 16 |  |  |  |
| Jul | Jul 17 | 100% |  |
| 15 |  |  |  |
| Jul | Jul 21 | 100% |  |
| 21 |  |  |  |
| Jul | Jul 21 | 100% |  |
| 21 |  |  |  |
| Jul | Jul 18 | 100% |  |
| 18 |  |  |  |
| Jul | Jul 22 | 100% |  |
| 22 |  |  |  |
| Jul | Jul 22 | 100% |  |
| 22 |  |  |  |
| Jul | Jul 21 | 100% |  |
| 21 |  |  |  |

| $0 | 4 days |
| --- | --- |
| $0 | 4 days |
| $0 | 4 days |
| $0 | 1 day |
| $0 | 1 day |
| $0 | 1 day |
| $0 | 3 days |
| $0 | 3 days |
| $0 | 3 days |
| $0 | 1 day |
| $0 | 1 day |
| $0 | 1 day |
| $0 | 1 day |
| $0 | 1 day |
| $0 | 1 day |

Jul 17

Jul 16

Jul 14

Jul 23

Jul 22

Jul 18

Jul 24

Jul 23

Jul 22

Jul 29

Jul 28

Jul 25

Jul 30

Jul 29

Jul 28

| Jul 22 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Jul 21 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 17 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 23 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 22 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 18 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 28 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 25 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 24 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 29 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 28 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 25 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 30 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 29 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| Jul 28 | 100% | $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |

| 72 | Documentation | 85 days |
| --- | --- | --- |
|  | Localize Code |  |
| 73 | Freeze | 47 days |
|  | Documentation |  |
|  | Localize French |  |
| 74 | Code Freeze | 45 days |
|  | Documentation |  |

Localize

| Feb | Jun 9 100% |  |  |
| --- | --- | --- | --- |
| 8 |  |  |  |
| Feb | Apr | 100% |  |
| 8 | 15 |  |  |
| Feb | Apr 15 100% |  |  |
| 8 |  |  |  |

| $260,026 | 85 days | Feb | Jun | 100% | $260,026 | $260,026 | $268,070 | ($8,044) | 103% | $0 | 0% | ($8,044) | 0.97 | 1.00 | $268,070 | $268,068 | $268,070 | 1.00 | 1.00 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 15 | 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| $160,876 | 47 days | Feb | Apr | 100% | $160,876 | $160,876 | $168,920 | ($8,044) | 105% | $0 | 0% | ($8,044) | 0.95 | 1.00 | $168,920 | $169,343 | $168,920 | 1.00 | 1.00 |  |
|  |  | 15 | 22 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| $48,263 | 45 days | Feb | Apr 22 100% |  | $48,263 | $48,263 | $50,676 | ($2,413) | 105% | $0 | 0% | ($2,413) | 0.95 | 1.00 | $50,676 | $50,803 | $50,676 | 1.00 | 1.00 |  |
|  |  | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PRO version  Are you a developer? Try out the HTML to PDF API	pdfcrowd.com

| 75 | German Code |  | 45 days |  | Feb |  | Apr 15 100% |  | $48,263 | 45 days |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Freeze |  |  |  | 8 |  |  |  |  |  |  |
|  | Documentation |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  |  |  |  |  |  |  |  |
| 76 | Japanese Code |  | 45 days |  | Feb |  | Apr 14 100% |  | $64,350 | 45 days |  |
|  | Freeze |  |  |  | 8 |  |  |  |  |  |  |
|  | Documentation |  |  |  |  |  |  |  |  |  |  |
| 77 |  |  |  |  |  |  |  |  |  |  |  |
| 78 | Localize Final |  | 13 days |  | Apr |  | May 1 100% |  | $99,150 | 15 days |  |
|  | Documentation |  |  |  | 15 |  |  |  |  |  |  |
|  | Localize |  |  |  | Apr |  |  |  |  |  |  |
| 79 | French Final |  | 12 days |  |  |  | May 1 100% |  | $30,045 | 12 days |  |
|  |  |  |  |  | 16 |  |  |  |  |  |  |
|  | Documentation |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  |  |  |  |  |  |  |  |
| 80 | French Final |  | 8 days |  | Apr |  | Apr 25 100% |  | $7,230 | 8 days |  |
|  | Getting Started |  |  |  | 16 |  |  |  |  |  |  |
|  | Guide |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  |  |  |  |  |  |  |  |
|  | French Final |  |  |  | Apr |  |  |  |  |  |  |
| 81 | Quick |  | 5 days |  |  |  | Apr 22 100% |  | $3,105 | 5 days |  |
|  | Reference |  |  |  | 16 |  |  |  |  |  |  |
|  | Guide |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  | Apr |  |  |  |  |  |  |
| 82 | French Final |  | 12 days |  |  |  | May 1 100% |  | $10,755 | 12 days |  |
|  |  |  |  |  | 16 |  |  |  |  |  |  |
|  | Using LullSIM |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  |  |  |  |  |  |  |  |
| 83 | French Final |  | 10 days |  | Apr |  | Apr 29 100% |  | $8,955 | 10 days |  |
|  | Administering |  |  |  | 16 |  |  |  |  |  |  |
|  | LullSIM |  |  |  |  |  |  |  |  |  |  |
| 84 |  |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  | Apr |  |  |  |  |  |  |
| 85 | German Final |  | 12 days |  |  |  | May 1 100% |  | $30,045 | 12 days |  |
|  |  |  |  |  | 16 |  |  |  |  |  |  |
|  | Documentation |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  |  |  |  |  |  |  |  |
| 86 | German Final |  | 8 days |  | Apr |  | Apr 25 100% |  | $7,230 | 8 days |  |
|  | Getting Start |  |  |  | 16 |  |  |  |  |  |  |
|  | Guide |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  |  |  |  |  |  |  |  |
|  | German Final |  |  |  | Apr |  |  |  |  |  |  |
| 87 | Quick |  | 5 days |  |  |  | Apr 22 100% |  | $3,105 | 5 days |  |
|  | Reference |  |  |  | 16 |  |  |  |  |  |  |
|  | Guide |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  | Apr |  |  |  |  |  |  |
| 88 | German Final |  | 12 days |  |  |  | May 1 100% |  | $10,755 | 12 days |  |
|  |  |  |  |  | 16 |  |  |  |  |  |  |
|  | Using LullSIM |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  |  |  |  |  |  |  |  |
| 89 | German Final |  | 10 days |  | Apr |  | Apr 29 100% |  | $8,955 | 10 days |  |
|  | Administering |  |  |  | 16 |  |  |  |  |  |  |
|  | LullSIM |  |  |  |  |  |  |  |  |  |  |
| 90 |  |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  | Apr |  |  |  |  |  |  |
| 91 | Japanese Final |  | 12 days |  |  |  | May 1 100% |  | $39,060 | 12 days |  |
|  |  |  |  |  | 15 |  |  |  |  |  |  |
|  | Documentation |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  |  |  |  |  |  |  |  |
| 92 | Japanese Final |  | 8 days |  | Apr |  | Apr 24 100% |  | $9,390 | 8 days |  |
|  | Getting Started |  |  |  | 15 |  |  |  |  |  |  |
|  | Guide |  |  |  |  |  |  |  |  |  |  |
|  | Localize |  |  |  |  |  |  |  |  |  |  |
|  | Japanese Final |  |  |  | Apr |  |  |  |  |  |  |
| 93 | Quick |  | 5 days |  |  |  | Apr 21 100% |  | $4,065 | 5 days |  |
| Reference |  | 15 |  |  |  |
| Guide |  |  |  |  |  |
| Localize |  | Apr |  |  |  |

| Feb | Apr 22 100% |  | $48,263 | $48,263 | $50,676 | ($2,413) | 105% | $0 | 0% | ($2,413) | 0.95 | 1.00 | $50,676 | $50,803 | $50,676 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Feb | Apr 18 100% |  | $64,350 | $64,350 | $67,568 | ($3,218) | 105% | $0 | 0% | ($3,218) | 0.95 | 1.00 | $67,568 | $67,737 | $67,568 |
| 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May 9 100% |  | $99,150 | $99,150 | $99,150 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $99,150 | $99,150 | $99,150 |
| 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May 9 100% |  | $30,045 | $30,045 | $30,045 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $30,045 | $30,045 | $30,045 |
| 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May 2 | 100% | $7,230 | $7,230 | $7,230 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $7,230 | $7,230 | $7,230 |
| 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | Apr 29 100% |  | $3,105 | $3,105 | $3,105 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $3,105 | $3,105 | $3,105 |
| 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May 9 100% |  | $10,755 | $10,755 | $10,755 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $10,755 | $10,755 | $10,755 |
| 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May 7 100% |  | $8,955 | $8,955 | $8,955 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $8,955 | $8,955 | $8,955 |
| 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May 9 100% |  | $30,045 | $30,045 | $30,045 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $30,045 | $30,045 | $30,045 |
| 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May 2 100% |  | $7,230 | $7,230 | $7,230 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $7,230 | $7,230 | $7,230 |
| 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | Apr 29 100% |  | $3,105 | $3,105 | $3,105 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $3,105 | $3,105 | $3,105 |
| 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May 9 100% |  | $10,755 | $10,755 | $10,755 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $10,755 | $10,755 | $10,755 |
| 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May 7 100% |  | $8,955 | $8,955 | $8,955 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $8,955 | $8,955 | $8,955 |
| 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May 8 100% |  | $39,060 | $39,060 | $39,060 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $39,060 | $39,060 | $39,060 |
| 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | May 1 100% |  | $9,390 | $9,390 | $9,390 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $9,390 | $9,390 | $9,390 |
| 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Apr | Apr 25 100% |  | $4,065 | $4,065 | $4,065 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $4,065 | $4,065 | $4,065 |
| 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Apr

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

- 1.00

PRO version  Are you a developer? Try out the HTML to PDF API	pdfcrowd.com

- Japanese Final 12 days Using LullSIM

Localize

- Japanese Final 10 days Administering

LullSIM

| 96 |  |  |  |
| --- | --- | --- | --- |
| 97 | QA Localized | 29 days |  |
|  | Documentation |  |  |

- Review French 26 days Documentation

Review French

- Getting Started 13 days Guide

Review French

| 100 | Quick | 5 days |  |
| --- | --- | --- | --- |
|  | Reference |  |  |

Guide

- Review French 20 days Using LullSIM

Review French

- Administering 15 days LullSIM

103

Review

104	German 26 days Documentation

Review

105	German 13 days Getting Started

Guide

Review

106	German Quick 5 days Reference

Guide

Review

107	German Using 20 days LullSIM

Review

108	German 15 days Administering

LullSIM

109

Review

110	Japanese 27 days Documentation

Review

111	Japanese 13 days Getting Started

Guide

Review

Japanese

112	Quick 5 days Reference

Guide

Review

113	Japanese 20 days Using LullSIM

Review

114	Japanese 15 days Administering

LullSIM

| 15 | May 1 100% |  |  |
| --- | --- | --- | --- |
| Apr | Apr 28 100% |  |  |
| 15 |  |  |  |
| Apr | Jun 2 100% |  |  |
| 22 |  |  |  |
| Apr | Jun 2 100% |  |  |
| 23 |  |  |  |
| Apr | May | 100% |  |
| 28 | 19 |  |  |
| Apr | Apr 29 100% |  |  |
| 23 |  |  |  |
| May | Jun 2 100% |  |  |
| 2 |  |  |  |
| Apr | May | 100% |  |
| 30 | 23 |  |  |
| Apr | May | 100% |  |
| 23 | 30 |  |  |
| Apr | May | 100% |  |
| 28 | 16 |  |  |
| Apr | Apr 29 100% |  |  |
| 23 |  |  |  |
| May | May | 100% |  |
| 2 | 30 |  |  |
| Apr | May | 100% |  |
| 30 | 22 |  |  |
| Apr | May | 100% |  |
| 22 | 30 |  |  |
| Apr | May | 100% |  |
| 25 | 15 |  |  |
| Apr | Apr 28 100% |  |  |
| 22 |  |  |  |
| May | May | 100% |  |
| 2 | 30 |  |  |
| Apr | May | 100% |  |
| 30 | 21 |  |  |

| $13,965 | 12 days | 21 | May 8 100% |  |  |
| --- | --- | --- | --- | --- | --- |
| $11,640 | 10 days | Apr | May 6 100% |  |  |
|  |  | 21 |  |  |  |
| $0 | 30 days | Apr | Jun 9 100% |  |  |
|  |  | 28 |  |  |  |
| $0 | 26 days | Apr | Jun 9 100% |  |  |
|  |  | 30 |  |  |  |
| $0 | 13 days | May | May | 100% |  |
|  |  | 5 | 23 |  |  |
| $0 | 5 days | Apr | May 7 100% |  |  |
|  |  | 30 |  |  |  |
| $0 | 20 days | May | Jun 9 | 100% |  |
|  |  | 13 |  |  |  |
| $0 | 15 days | May | May | 100% |  |
|  |  | 9 | 30 |  |  |
| $0 | 27 days | Apr | Jun 9 100% |  |  |
|  |  | 30 |  |  |  |
| $0 | 13 days | May | May | 100% |  |
|  |  | 5 | 22 |  |  |
| $0 | 5 days | Apr | May 7 100% |  |  |
|  |  | 30 |  |  |  |
| $0 | 20 days | May | Jun 9 | 100% |  |
|  |  | 13 |  |  |  |
| $0 | 15 days | May | May | 100% |  |
|  |  | 8 | 29 |  |  |
| $0 | 27 days | Apr | Jun 5 100% |  |  |
|  |  | 28 |  |  |  |
| $0 | 13 days | May | May | 100% |  |
|  |  | 2 | 21 |  |  |
| $0 | 5 days | Apr | May 6 100% |  |  |
|  |  | 28 |  |  |  |
| $0 | 20 days | May | Jun 5 | 100% |  |
|  |  | 9 |  |  |  |
| $0 | 15 days | May | May | 100% |  |
|  |  | 7 | 27 |  |  |

| $13,965 | $13,965 | $13,965 | $0 | 100% $0 0% $0 |  |  |  | 1.00 | 1.00 | $13,965 | $13,965 | $13,965 | 1.00 | 1.00 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| $11,640 | $11,640 | $11,640 | $0 | 100% | $0 | 0% | $0 | 1.00 | 1.00 | $11,640 | $11,640 | $11,640 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |

PRO version  Are you a developer? Try out the HTML to PDF API	pdfcrowd.com

| 115 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 116 | Correct French | 5 days | Jun | Jun 9 | 100% | $0 |  |
|  | Documentation |  | 3 |  |  |  |  |
| 117 | Correct German | 5 days | Jun | Jun 9 | 100% | $0 |  |
|  | Documentation |  | 3 |  |  |  |  |
| 118 | Correct Japanese | 5 days | Jun | Jun 6 | 100% | $0 |  |
|  | Documentation |  | 2 |  |  |  |  |
| 119 |  |  |  |  |  |  |  |
| 120 | Online Help | 11 days | Jun | Jun | 100% | $8,000 |  |
|  |  |  | 9 | 23 |  |  |  |
| 121 | Convert French | 5 days | Jun | Jun 16 100% |  | $2,400 |  |
|  | Online Help |  | 10 |  |  |  |  |
| 122 | Convert German | 5 days | Jun | Jun 16 100% |  | $2,400 |  |
|  | Online Help |  | 10 |  |  |  |  |
|  | Convert |  | Jun |  |  |  |  |
| 123 | Japanese Online | 5 days |  | Jun 13 100% |  | $3,200 |  |
|  | Help |  | 9 |  |  |  |  |
| 124 |  |  |  |  |  |  |  |
| 125 | Review French | 4 days | Jun | Jun 20 100% |  | $0 |  |
|  | Online Help |  | 17 |  |  |  |  |
| 126 | Review German | 4 days | Jun | Jun 20 100% |  | $0 |  |
|  | Online Help |  | 17 |  |  |  |  |
| 127 | Review Japanese | 4 days | Jun | Jun 19 100% |  | $0 |  |
|  | Online Help |  | 16 |  |  |  |  |
| 128 |  |  |  |  |  |  |  |

| 5 days | Jun | Jun 16 100% |  | $0 |
| --- | --- | --- | --- | --- |
|  | 10 |  |  |  |
| 5 days | Jun | Jun 16 100% |  | $0 |
|  | 10 |  |  |  |
| 5 days | Jun | Jun 12 100% |  | $0 |
|  | 6 |  |  |  |
| 12 days | Jun | Jun | 100% | $8,000 |
|  | 13 | 30 |  |  |
| 5 days | Jun | Jun 23 100% |  | $2,400 |
|  | 17 |  |  |  |
| 5 days | Jun | Jun 23 100% |  | $2,400 |
|  | 17 |  |  |  |
| 5 days | Jun | Jun 19 100% |  | $3,200 |
|  | 13 |  |  |  |
| 4 days | Jun | Jun 27 100% |  | $0 |
|  | 24 |  |  |  |
| 4 days | Jun | Jun 27 100% |  | $0 |
|  | 24 |  |  |  |
| 4 days | Jun | Jun 25 100% |  | $0 |
|  | 20 |  |  |  |

| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | 0% | $0 0% $0 |  |  | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $8,000 | $8,800 | ($800) | 110% $0 0% ($800) |  |  |  | 0.91 | 1.00 | $8,800 | $8,791 | $8,800 | 1.00 | 1.00 |
| $2,400 | $2,640 | ($240) | 110% $0 0% ($240) |  |  |  | 0.91 | 1.00 | $2,640 | $2,637 | $2,640 | 1.00 | 1.00 |
| $2,400 | $2,640 | ($240) | 110% $0 0% ($240) |  |  |  | 0.91 | 1.00 | $2,640 | $2,637 | $2,640 | 1.00 | 1.00 |
| $3,200 | $3,520 | ($320) | 110% | $0 | 0% | ($320) | 0.91 | 1.00 | $3,520 | $3,516 | $3,520 | 1.00 | 1.00 |
| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |

| 129 | Correct French | 1 day |  |
| --- | --- | --- | --- |
|  | Online Help |  |  |
| 130 | Correct German | 1 day |  |
|  | Online Help |  |  |

- Correct Japanese 1 day Online Help

132

| Jun | Jun 23 100% | $0 |
| --- | --- | --- |
| 23 |  |  |
| Jun | Jun 23 100% | $0 |
| 23 |  |  |
| Jun | Jun 20 100% | $0 |
| 20 |  |  |

| 1 day | Jun | Jun 30 100% | $0 |
| --- | --- | --- | --- |
|  | 30 |  |  |
| 1 day | Jun | Jun 30 100% | $0 |
|  | 30 |  |  |
| 1 day | Jun | Jun 26 100% | $0 |
|  | 26 |  |  |

| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |

|  | Marketing |  | May Jun |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 133 | Communications 24 days |  |  |  | 100% | $11,224 |  |
|  |  |  | 22 | 25 |  |  |  |
|  | (MarCOM) |  |  |  |  |  |  |
|  | Localize French |  | May May |  |  |  |  |
| 134 | MarCOM | 6 days |  |  | 100% | $3,308 |  |
|  |  |  | 22 | 29 |  |  |  |
|  | Materials |  |  |  |  |  |  |
|  | Localize German |  | May May |  |  |  |  |
| 135 | MarCOM | 6 days |  |  | 100% | $3,308 |  |
|  |  |  | 22 | 29 |  |  |  |
|  | Materials |  |  |  |  |  |  |
|  | Localize |  |  |  |  |  |  |
| 136 | Japanese | 8 days | Jun | Jun 20 100% |  | $4,608 |  |
|  | MarCOM |  | 11 |  |  |  |  |
|  | Materials |  |  |  |  |  |  |
| 137 |  |  |  |  |  |  |  |
|  | Review French |  | May |  |  |  |  |
| 138 | MarCOM | 2 days |  | Jun 2 | 100% | $0 |  |
|  | Materials |  | 30 |  |  |  |  |
|  | Review German |  | May |  |  |  |  |
| 139 | MarCOM | 2 days |  | Jun 2 | 100% | $0 |  |
|  | Materials |  | 30 |  |  |  |  |
|  | Review Japanese |  | Jun |  |  |  |  |
| 140 | MarCOM | 2 days |  | Jun 24 100% |  | $0 |  |
|  | Materials |  | 23 |  |  |  |  |
| 141 |  |  |  |  |  |  |  |
|  | Correct French |  | Jun |  |  |  |  |
| 142 | MarCOM | 1 day |  | Jun 3 | 100% | $0 |  |
|  | Materials |  | 3 |  |  |  |  |
|  | Correct German |  | Jun |  |  |  |  |
| 143 | MarCOM | 1 day |  | Jun 3 | 100% | $0 |  |
|  |  |  | 3 |  |  |  |  |

| 21 days | May | Jun | 100% | $11,224 |  |
| --- | --- | --- | --- | --- | --- |
|  | 28 | 25 |  |  |  |
| 6 days | May | Jun 5 | 100% | $3,308 |  |
|  | 28 |  |  |  |  |
| 6 days | May | Jun 5 | 100% | $3,308 |  |
|  | 28 |  |  |  |  |
| 8 days | Jun | Jun 20 100% |  | $4,608 |  |
|  | 11 |  |  |  |  |
| 2 days | Jun | Jun 9 | 100% | $0 |  |
|  | 6 |  |  |  |  |
| 2 days | Jun | Jun 9 | 100% | $0 |  |
|  | 6 |  |  |  |  |
| 2 days | Jun | Jun 24 100% |  | $0 |  |
|  | 23 |  |  |  |  |
| 1 day | Jun | Jun 10 100% |  | $0 |  |
|  | 10 |  |  |  |  |
| 1 day | Jun | Jun 10 100% |  | $0 |  |
|  | 10 |  |  |  |  |

| $11,224 | $13,470 | ($2,246) | 120% $0 0% ($2,246) |  |  |  | 0.83 | 1.00 | $13,470 | $13,523 | $13,470 | 1.00 | 1.00 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| $3,308 | $3,970 | ($662) | 120% $0 0% ($662) |  |  |  | 0.83 | 1.00 | $3,970 | $3,986 | $3,970 | 1.00 | 1.00 |
| $3,308 | $3,970 | ($662) | 120% $0 0% ($662) |  |  |  | 0.83 | 1.00 | $3,970 | $3,986 | $3,970 | 1.00 | 1.00 |
| $4,608 | $5,530 | ($922) | 120% | $0 | 0% | ($922) | 0.83 | 1.00 | $5,530 | $5,552 | $5,530 | 1.00 | 1.00 |
| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |

PRO version  Are you a developer? Try out the HTML to PDF API	pdfcrowd.com

|  | Materials |  |  |
| --- | --- | --- | --- |
|  | Correct Japanese |  |  |
| 144 | MarCOM | 1 day |  |
|  | Materials |  |  |
| 145 |  |  |  |
| 146 | Manufacturing | 35 days |  |
|  | Release To |  |  |
| 147 | Manufacturing | 1 day |  |
|  | French MarCOM |  |  |
|  | Materials |  |  |
|  | Release To |  |  |
| 148 | Manufacturing | 1 day |  |
|  | German MarCOM |  |  |
|  | Materials |  |  |
|  | Release To |  |  |
|  | Manufacturing |  |  |
| 149 | Japanese | 1 day |  |
|  | MarCOM |  |  |
|  | Materials |  |  |
| 150 |  |  |  |
|  | Release To |  |  |
| 151 | Manufacturing | 1 day |  |
|  | French |  |  |
|  | Documentation |  |  |
|  | Release To |  |  |
| 152 | Manufacturing | 1 day |  |
|  | German |  |  |
|  | Documentation |  |  |
|  | Release To |  |  |
| 153 | Manufacturing | 1 day |  |
|  | Japanese |  |  |
|  | Documentation |  |  |
| 154 |  |  |  |
|  | Release To |  |  |
| 155 | Manufacturing | 1 day |  |
|  | French Gold |  |  |
|  | Master ISO Image |  |  |
|  | Release To |  |  |
| 156 | Manufacturing | 1 day |  |
|  | German Gold |  |  |
|  | Master ISO Image |  |  |
|  | Release To |  |  |
| 157 | Manufacturing | 1 day |  |
|  | Japanese Gold |  |  |
|  | Master ISO Image |  |  |
| 158 |  |  |  |
| 159 | Translation | 3 days |  |
|  | Memory |  |  |
|  | Compile French |  |  |
| 160 | Translation | 1 day |  |
|  | Memory |  |  |
|  | Compile German |  |  |
| 161 | Translation | 1 day |  |
|  | Memory |  |  |
|  | Compile |  |  |
| 162 | Japanese | 1 day |  |
|  | Translation |  |  |
|  | Memory |  |  |
| 163 |  |  |  |
|  | Launch LullSIM in |  |  |
| 164 | France, Germany, | 5 days |  |

| Jun | Jun 25 100% |  | $0 |  |
| --- | --- | --- | --- | --- |
| 25 |  |  |  |  |
| Jun | Jul 23 100% |  | $0 |  |
| 4 |  |  |  |  |
| Jun | Jun 4 | 100% | $0 |  |
| 4 |  |  |  |  |
| Jun | Jun 4 | 100% | $0 |  |
| 4 |  |  |  |  |
| Jun | Jun 26 100% |  | $0 |  |
| 26 |  |  |  |  |
| Jun | Jun 24 100% |  | $0 |  |
| 24 |  |  |  |  |
| Jun | Jun 24 100% |  | $0 |  |
| 24 |  |  |  |  |
| Jun | Jun 23 100% |  | $0 |  |
| 23 |  |  |  |  |
| Jul | Jul 23 | 100% | $0 |  |
| 23 |  |  |  |  |
| Jul | Jul 23 | 100% | $0 |  |
| 23 |  |  |  |  |
| Jul | Jul 22 | 100% | $0 |  |
| 22 |  |  |  |  |
| Jun | Jun | 100% | $0 |  |
| 25 | 27 |  |  |  |
| Jun | Jun 25 100% |  | $0 |  |
| 25 |  |  |  |  |
| Jun | Jun 25 100% |  | $0 |  |
| 25 |  |  |  |  |
| Jun | Jun 27 100% |  | $0 |  |
| 27 |  |  |  |  |
| Jul | Jul 30 | 100% | $0 |  |
| 24 |  |  |  |  |

| 1 day | Jun | Jun 25 100% |  |  |
| --- | --- | --- | --- | --- |
|  | 25 |  |  |  |
| 36 days | Jun | Jul 31 100% |  |  |
|  | 11 |  |  |  |
| 1 day | Jun | Jun 11 100% |  |  |
|  | 11 |  |  |  |
| 1 day | Jun | Jun 11 100% |  |  |
|  | 11 |  |  |  |
| 1 day | Jun | Jun 26 100% |  |  |
|  | 26 |  |  |  |
| 1 day | Jul 1 | Jul 1 | 100% |  |
| 1 day | Jul 1 | Jul 1 | 100% |  |
| 1 day | Jun | Jun 27 100% |  |  |
|  | 27 |  |  |  |
| 1 day | Jul | Jul 31 | 100% |  |
|  | 31 |  |  |  |
| 1 day | Jul | Jul 30 | 100% |  |
|  | 30 |  |  |  |
| 1 day | Jul | Jul 29 | 100% |  |
|  | 29 |  |  |  |
| 3 days | Jun | Jul 2 | 100% |  |
|  | 30 |  |  |  |
| 1 day | Jul 2 | Jul 2 | 100% |  |
| 1 day | Jul 2 | Jul 2 | 100% |  |
| 1 day | Jun | Jun 30 100% |  |  |
|  | 30 |  |  |  |
| 5 days | Aug | Aug 7 100% |  |  |
|  | 1 |  |  |  |

| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |
| $0 | $0 | $0 | $0 | 0% | $0 | 0% | $0 | 1.00 | 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |

PRO version  Are you a developer? Try out the HTML to PDF API	pdfcrowd.com

|  | Japan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 165 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Project Complete, | Jul |  |  |  | Aug |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 166 | Conduct Lessons 1 day |  | Jul 31 100% | $0 | 1 day |  | Aug 8 100% | $0 | $0 | $0 | $0 | 0% | $0 0% $0 | 1.00 1.00 | $0 | $0 | $0 | 1.00 | 1.00 |  |
|  | Learned | 31 |  |  |  | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PRO version  Are you a developer? Try out the HTML to PDF API	pdfcrowd.com