Background

The Custom Woodworking Company is a small-to-medium sized custom furniture and cabinet making

company, with head-office and a spacious plant site at Industrial Estates, Someplace, BC. Its

Chairman and Chief Executive Officer is Ron Carpenter now in his late-sixties. His wife Mrs. Emelia

Carpenter, being an aggressive business woman and somewhat younger than her husband, now

effectively runs the company.

Ron Carpenter is affectionately known to all as "Woody" and so the company is generally known as

"Woody's". Woody, after an apprenticeship as a cabinet maker, started his small furniture

manufacturing business back in 1954 and he and his wife moved to their present location in 1959.

The company quickly gained a reputation for attractively designed and well constructed furniture,

using imported hardwoods and indigenous softwoods for its products. Woody's now produces custom

furniture to order, several lines of furniture for wholesaler/retailers, and a number of variations

of standard kitchen and bathroom cabinets, including units made to order.

Over the years the Carpenters continued to prosper and built up a loyal staff and work force. More

recently their son, John Carpenter, has joined the company's management after having obtained a

commerce degree at the local university. At John Carpenter's insistence, lured by longer production

runs and higher and more consistent mark-ups, the company has moved into subcontract work supplying

and installing counter-tops, cabinets and similar fixtures for new commercial construction. To

date, Woody's has established a well-founded reputation for supplying millwork to the construction

industry.

Woody's Corporate Profile

Head Office:

Someplace, BC

Business:Ý

Furniture manufacturing, custom millwork, and hardwood importer; federal charter 1960; privately

held; number of employees approx. 850. Major Shareholder: Emelia Holdings Ltd. At December 31,

199X, total assets were $181,000,000. In fiscal 199X, sales were $93,250,000 with net earnings of

$6,540,000.

Directors:

Chairman & CEOÝ

Ron Carpenter

President

Mrs. Emelia Carpenter

Executive Vice President

Kim Qualey

Director

John Carpenter

Key Personnel:

VP Production

Miles Faster

VP Finance and Administration

Spencer Moneysworth

VP Personnel

Molly Bussell

VP Sales and Estimating

Bruce Sharpe

Controller

Kim Cashman

Other Key Players in this Case Study:

I. Leadbetter (Ian)

Woody's Project Manager

R. Schemers (Randy)

Principal, Schemers and Plotters (S&P), industrial design consultants

A. Fowler (Alfred)

Director, Expert Industrial Developers (EID), industrial property developers and contractors

I. Kontrak (Ivar)

EID's Project Manager

D. Rivett (Dave)

I. Beam Construction Ltd., steel fabricators and installers

B. Leakey (Bert)

Classic Cladding Co., cladding and roofing contractors

C. Droppe (Charlie)

I. C. Rain Ltd., water-proofing contractors

A. Dent (Amos)

Tinknockers Associates, mechanical contractors

O. Volta (Olaf)

Zapp Electric Co., electrical contractors

E. Forgot (Eddie)

Piecemeal Corporation, equipment suppliers

W. Easley (Win)

Project management consultants

The Opportunity

In 1989 there was a mini-boom in commercial construction in south-western BC. With the possibility

of a major airport expansion, and free-trade opportunities south of the border, Bruce Sharpe

persuaded Woody's directors that they were well placed to expand their manufacturing business.

Miles Faster, regularly complaining that the company's production efficiency was being thwarted by

lack of manufacturing space, made a pitch to John Carpenter for moving to completely new and more

modern facilities. John Carpenter, with a vision of growth based on computer controlled automation,

talked over the idea with his father. Woody discussed it with his wife who in turn brought Kim

Cashman and Spencer Moneysworth into the debate.

Cashman and Moneysworth felt strongly that they should remain where they were, since there was

spare land on their property, even though not the most convenient for plant expansion. They argued

that not only would this avoid the costs of buying and selling property, but more importantly avoid

the interruption to production while relocating their existing equipment. Besides, the nearest

potential location at an attractive price was at least fifteen miles further out from the

residential area where most of them lived. Polarization of opinions rapidly became evident and so,

in the spring of 1989, Woody called a meeting of the directors and key personnel to resolve the

issue. After a visit to the factory floor and a prolonged and sometimes bitter argument lasting

into the early hours, it was agreed that the company would stay put on its existing property.

The Project Concept

It was agreed at the meeting that additional production capacity would be added equivalent to 25%

of the existing floor area. The opportunity would also be taken to install air-conditioning and a

dust-free paint and finishing shop complete with additional compressor capacity. Equipment would

include a semi-automatic woodworking production train, requiring the development and installation

of software and hardware to run it. The President and Executive Vice Presidents' offices would also

be renovated.

At the meeting, the total cost of the work, not including office renovation, was roughly estimated

at $17 million. Woody agreed to commit the company to a budget of $17 million as an absolute

maximum for all proposed work and the target date for production would be eighteen months from now.

To give Woody's personnel a feeling of ownership, Molly Bussell proposed that the project should be

called Woody 2000. Spencer Moneysworth would take responsibility for Project Woody 2000.

Planning

Moneysworth was keen to show his administrative abilities. He decided not to involve the production

people as they were always too busy and, anyway, that would only delay progress. So, not one for

wasting time (on planning) Moneysworth immediately invited Expert Industrial Developers (EID) to

quote on the planned expansion. He reasoned that this contractor's prominence on the industrial

estate and their knowledge of industrial work would result in a lower total project cost.

Meanwhile, Kim Cashman developed a monthly cash flow chart as follows. First he set aside one

million for contingencies. Then he assumed that expenditure would be one million in each of the

first and last months, with an intervening ten months at $1.4 million. He carefully locked the

chart away in his drawer for future reference. All actual costs associated with the project would

be recorded as part of the company's normal book-keeping.

Upon Moneysworth's insistence, EID submitted a fixed-price quotation. It amounted to $20 million

and an eighteen month schedule. After Moneysworth recovered from the shock, he persuaded Woody's

management that the price and schedule were excessive. (For their part, EID believed that Woody's

would need considerable help with their project planning and allowed for a number of

uncertainties). Further negotiations followed in which EID offered to undertake the work based on a

fully reimbursable contract.

Moneysworth started inquiries elsewhere but EID countered with an offer to do their own work on

cost plus but solicit fixed price quotations for all sub-trade work. Under this arrangement EID

would be paid an hourly rate covering direct wages or salaries, payroll burden, head-office

overhead and profit. This rate would extend to all engineering, procurement, construction and

commissioning for which EID would employ Schemers and Plotters (S&P) for the building and

industrial design work. Moneysworth felt that the proposed hourly rate was reasonable and that the

hours could be monitored effectively. He persuaded Woody's directors to proceed accordingly.

The Design

A couple of months later as S&P commenced their preliminary designs and raised questions and issues

for decision, Moneysworth found he needed assistance to cope with the paper work. John Carpenter

suggested he use Ian Leadbetter, a bright young mechanical engineer who had specialized in

programming semi-automatic manufacturing machinery. Moneysworth realized that this knowledge would

be an asset to the project and gave Leadbetter responsibility for running the project. Ian was keen

to demonstrate his software skills to his friend John Carpenter. So, while he lacked project

management training and experience (especially any understanding of "project life-cycle" and

"control concepts") he readily accepted the responsibility.

During the initial phases of the mechanical design, Ian Leadbetter made good progress on developing

the necessary production line control software program. However, early in design EID suggested that

Woody's should take over the procurement of the production train directly, since they were more

knowledgeable of their requirements. Miles Faster jumped at the opportunity to get involved and

decided to change the production train specification to increase capacity. Because of this, the

software program had to be mostly rewritten, severely limiting Leadbetter's time for managing the

project. It also resulted in errors requiring increased debugging at startup.

Neither Moneysworth nor Leadbetter was conscious of the need for any review and approval procedures

for specifications and shop drawings submitted directly by either S&P or by Eddie Forgot of

Piecemeal Corporation, the suppliers of the production train. In one two-week period, during which

both Faster and Leadbetter were on vacation, the manufacturing drawings for this critical long-lead

equipment sat in a junior clerk's in-tray awaiting approval. For this reason alone, the delivery

schedule slipped two weeks, contributing to a later construction schedule conflict in tying-in the

new services.

Construction

Site clearing was tackled early on with little difficulty. However, as the main construction got

into full swing some eight months later, more significant problems began to appear. The change in

production train specification made it necessary to add another five feet to the length of the new

building. This was only discovered when holding-down bolts for the new train were laid out on site,

long after the perimeter foundations had been poured. The catalogue descriptions and specifications

for other equipment selected were similarly not received and reviewed until after the foundations

had been poured.

Leadbetter was not entirely satisfied with the installation of the mechanical equipment for the

dust-free paint shop. As a registered mechanical engineer, he knew that the specifications governed

the quality of equipment, workmanship and performance. However, since these documents had still not

been formally approved, he was loath to discuss the matter with Ivar Kontrak. Instead, he dealt

directly with Amos Dent of Tinknockers Associates, the mechanical sub-contractor. This led to

strained relations on the site.

Another difficulty arose with the paint shop because the local inspection authority insisted that

the surplus paint disposal arrangements be upgraded to meet the latest environmental standards.

Startup

Two years after the project was first launched, the time to get the plant into production rapidly

approached. However, neither Moneysworth nor Leadbetter had prepared any meaningful planning for

completion such as owner's inspection and acceptance of the building, or testing, dry-running and

production start-up of the production train. They also failed to insist that EID obtain the

building occupation certificate. Moreover, due to late delivery of the production train, the

"tie-in" of power and other utility connections scheduled for the annual two-week maintenance

shut-down could not in fact take place until two weeks later.

These factors together resulted in a loss of several weeks of production. Customer delivery dates

were missed and some general contractors cancelled their contracts and placed their orders for

millwork elsewhere. Finished goods inventories were depleted to the point that other sales

opportunities were also lost in the special products areas on which Woodyís reputation was based.

Control

Costs arising from these and other changes, including the costs of delays in completion, were

charged to Woody's account. Project overrun finally became reality when actual expenditures

exceeded the budget and it was apparent to everyone that the project was at best only 85% complete.

Cashman was forced to scramble for an additional line of credit in project financing at prime plus

2-1/2%, an excessive premium given Woody's credit rating. From then on, Woody's were in a fire

fighting mode and their ability to control the project diminished rapidly. They found themselves

throwing money at every problem in an effort to get the plant operational.

During Woodyís period of plant upgrading, construction activity in the region fell dramatically

with general demand for Woodyís products falling similarly. Even though Sharpe launched an

expensive marketing effort to try to regain customer loyalty, it had only a marginal effect.

Post Project Appraisal

The net result was that when the new equipment eventually did come on stream, it was seriously

under utilized. Production morale ebbed. Some staff publicly voiced their view that the over-supply

of commercial space could have been foreseen even before the project started, especially the

oversupply of retail and hotel space, the prime source of Woody's contracts. John Carpenter, not a

favorite with the older staff, was blamed for introducing these "new fangled and unnecessarily

complicated ideas".

Because of this experience, Woody's President Emelia Carpenter retained project management

consultant Win Easley of W. Easley Associates to conduct a post project appraisal. Easley had some

difficulty in extracting solid information because relevant data was scattered amongst various

staff, who were not keen to reveal their short-comings. Only a few formal notes of early project

meetings could be traced. Most of the communication was on hand-written Speedy memos, many of which

were undated. However, interviews with the key players elicited considerable information, as has

been outlined above.

Case Study Exercise

The incidents described in this case study are typical of the types of things that happen in

real-life projects. They are a reflection of peoples' attitudes and the way they do things. Perhaps

they do not all happen on the same project. Yet the reality is that if project sponsors do not

start out with an understanding of project management and its processes, the probability of these

kinds of happenings are quite high! One of the best ways of learning is from mistakes ó preferably

from those of other people.

The focus of this case study centers on construction. However, the project has served to bring to

light many of Woody's management short-comings and the need for change. Can you spot the real

source of the problems and what needs to be done to fix them?

Your task is to show how you would run this project properly from the beginning.

Project Appraisal Questionnaire

The purpose of project management is to achieve a successful project and all that this implies. So,

if you were Win Easley, the project management consultant, what would you report? Specific issues

for your consideration follow. You will not find all the answers written into the case study. Most

of the answers are matters of opinion and you will need to search the text book  for ways to

approach many of them.