## Sheet1
Problem #14: Page 186
Name:
|  |  | Early | Early | Late | Late |  | Critical
| Activity | Duration | Start | Finish | Start | Finish | Slack | Path?
| 1) Problem Definition | 2
| 2) System Analysis | 5
| 3) Design Input & Output | 3
| 4) Design Database | 15
| 5) Develop Input Screens | 8
| 6) Develop Output Reports | 10
| 7) Develop Database | 2
| 8) Test System | 6
| 9) Implement System | 5
Finish in 30 weeks?
Critical Path?